{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":24,"n_cols":3,"rows_kept":24,"cut":false,"hidden":false,"merged":[[0,0,0,16383],[7,0,7,3]]}
["\n                                             工作周报"]
["时间","完成情况","总结（上周遇到的问题以及版本延期的原因）"]
["2018.5.28--2018.6.2\n （乐外卖2.4.0版本）\n","熟悉需求和原型交互，才刚刚开始测试后端","开发没有给到一个可以测的模块，测试这边现在针对这个版本只能零零散散的测试，测试进度缓慢"]
["2018.5.28--2018.6.2\n （乐外卖2.6.0版本）\n","1.前端小程序，同城信息只测了招聘全职和兼职\n2.后台功能方面测了同城信息管理、信息设置、信息审批、信息举报","其它模块还在研发中，测试进度占总体的10%"]
["2018.5.28--2018.6.2\n （智铺子2.6.0版本）","熟悉需求和原型交互","开发还没有开发完成待测功能，待测"]
["2018.5.28--2018.6.2\n （智铺子2.7.0版本）","熟悉需求和原型交互\n\n","开发还没有开发完成待测功能，待测"]
["2018.5.28--2018.6.2\n （智铺子2.8.0版本）\n","已发版","总共测试出18个bug，其中严重bug9个，一般bug9个"]
["修复bugfix版本人力情况"]
["名称","版本","工作量"]
["黄牛超","乐外卖--bugfix---2.0.8",0.2]
["乔光","乐外卖--bugfix---2.0.8",4]
["马伟","乐外卖--bugfix---2.0.8",8]
["张尤俊","乐外卖--bugfix---2.0.8",2]
["侯兴宇","乐外卖--bugfix---2.0.8",1]
["吴永展","乐外卖--bugfix---2.0.8",11]
["宋俊辉","乐外卖--bugfix---2.0.8",1]
["谢烨飞","乐外卖--bugfix---2.0.8",3.5]
["王思校","乐外卖--bugfix---2.0.8",2]
["袁宇","乐外卖--bugfix---2.0.8",1]
[" 舒欣","智铺子--bugfix---2.0.6",11]
["林澄宇","智铺子--bugfix---2.0.6",3]
["廖桃","智铺子--bugfix---2.0.6",2]
["杜笛","智铺子--bugfix---2.0.6",1]
["李冠京","智铺子--bugfix---2.0.6",2]

{"sheet":"Sheet2","index":1,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["1.下载列表显示功能\n2.修复在5.0及以上的手机系统版本上，应用内广告无法展示的问题\n3.拉广告，拉配置上行加了系统软件版本参数（sysVersion）屏蔽系统软件版本功能\n4.mid加入白名单后上传日志的功能 \n5.拉活跃功能\n6.优化URL跳转失败问题 \n7.小图标放大\n8.icon文件夹问题优化（只支持URL广告，非URL类型全部过滤不显示）\n9.更新了快捷方式的删除方法（创建前先删除）\n10.KY的JAR上验证拉活提醒，当广告A配置了打开提醒，拉活不活跃周期设置为4天，安装广告A的时间点为T，当T+2天时展示打开提醒并打开广告A，当T+4后仍然展示拉活提醒，应该在T+6天才能展示拉活提醒\n11.数据统计核对，特别是弹出系统安装，安装完后点打开，OPEN数据的上报\n12.在KY的桌面上也会出现ICON文件夹重复创建的问题\n13.在各机型上测试酷宇桌面，看是否能启动爱告服务"]

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}